## Sheet1
Optimising Flight Paths for Transatlantic Flights with Simulation | (Starting Week December 21) Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Implement the Globe | bar: Week 2
Implement a Great Circle | bar: Week 2 to Week 3
Report the implementation process of the globe and the math involved | bar: Week 3 to Week 5
Create the aircraft, get statistics, report | bar: Week 4 to Week 6
Test a simple flight using an unaltered great circle | bar: Week 5 to Week 6
Adjust air speeds, flight level, aircraft weight, fuel consumption etc. | bar: Week 6 to Week 7
Run tests again, start visualising these tests, graphs, report | bar: Week 6 to Week 8
Implement jet streams and weather conditions | bar: Week 7 to Week 8
Advanced fuel consumption | bar: Week 7 to Week 10
Analyse variables and add the minor onces | bar: Week 9 to Week 11
Identify changes on the minor variables, add or remove, report | bar: Week 8 to Week 10
Start linking variables in the simulation | bar: Week 9 to Week 10
Implement optimisation techniques and report the results | bar: Week 10 to Week 12
Data analysis and real-life data comparison | bar: Week 10 to Week 12